## Acceptance - Key tasks and V&V
Acceptance and Signoff sheet for Transition
Application Name: | VIP Logistica - Portos
Vale Team: | Wildo Martins / Carla Manchesi / Lucio Wagner
TCS Team : | Marcelo Mello / Michele Martins / Graziella Paneto
Accenture Team: | Emanuel Stein / Geydel Marozzi
Acronyms
V – Verify
A – Approve
X – Indicates type of the activity to be closed
Startup Activities: 11/02/19 a 18/02/19
Activities | Vale |  | Approval by Vale | Remarks
Startup | V | A
Discuss Approach, Procedures and detailed plan |  | X
Update procedures in detailed plan, if required |  | X
Sign-Off | V | A
Access to environment and infrastructure | X
Documentation consolidation (sent from Vale/Vendor) |  | X
Transition Governance Setup |  | X
Transition Plan sign-off |  | X
Knowledge Transfer (KT) - Execution Phase Activities: 07/03/19
Activities | Vale |  | Approval by Vale | Remarks
Organization Chart | V | A
Prepare project organization chart | X
Existing process and environment | V | A
Create Documents of Understanding (DOU) to the Application |  | X
Testing Procedures | V | A
Document Testing Procedures in Documents of Understanding | X
Document analysis and Organization (for each module) | V | A
Prepare/Update the Documents of Understanding - System Description |  | X
Prepare/Update Documents of Understanding - Overview docs on missing module specifications | NA
Database analysis (for each Sub applications/module) | V | A
Update Documents of Understanding - Database Analysis |  | X
Update Inventory (for each Sub Applications/module) | V | A
Prepare/update the Documents of Understanding - System Inventory details | X
Coding Standards | V | A
Understand coding standards document for future development and enhancements | X
Prepare/Update the Documents of Understanding for Coding Standards | X
Analysis of Maintenance History | V | A
Identify number of problems and enhancements performed over a period of time |  | X
Study the manner in which the problems were closed |  | X
Prepare a detailed activity list on Maintenance and Support and Development that are carried out by Client and update Documents of Understanding |  | X
Analysis of Help-Desk Methodology | V | A
Identify number of issues resolved |  | X
Study how problems were received/resolved/closed |  | X
Prepare a detailed activity list on helpdesk activities that are carried out by Client |  | X
Operations Procedures Study | V | A
Study coding standards and naming conventions | X
Defect Logging and Monitoring | V | A
Prepare Defect Logging and Monitoring procedures for Acceptance Phase in Documents of Understanding | NA
Acceptance Procedures | V | A
Document Acceptance Procedures in Documents of Understanding |  | X
Existing Vendor interaction | V | A
Document Vendor Liaison Procedures in Documents of Understanding |  | X
Finalize Manuals | V | A
Finalize Documents of Understanding |  | X
Finalize Knowledge-Base Document | NA
Study existing development projects | V | A
Prepare a development take-on plan for assuming responsibility of development |  | X
Transition Plan (Progress Monitoring) | V | A
Update Transition Plan based on the project progress and changes in scope of the project |  | X
Weekly Reviews and Play back Session |  | X
Signoff play back section |  | X
Recorded KT Sessions | V | A
All recorded KT sessions organized and available |  | X
Sign-Off | V | A
Timely completion of KT sessions |  | X
TCS Complete understanding of Aplication Services |  | X
Draft DOU Signoff |  | X
Vale final signoff |  | X
Activities for Shadow Support
Activities | Vale |  | Approval by Vale | Remarks
Support for Maintenance activities | V | A
Request read only access for App environments
TCS to provide Secondary support
Provide fixes to assigned incident tickets
Review fixes for incident assigned to TCS
Support for Development activities | V | A
Understand the – Functional Specification, Low Level Design, Technical Specifications coding, unit testing, etc.
Refine Manuals | V | A
Review and release Documents of Understanding
Sign-Off | V | A
50% retention of new P3 + P4 incidents (opened during shadow phase);
Readiness results for operational processes
Sign off Secondary Support Phase
Activities for Shadow Reverse
Activities | Vale |  | Approval by Vale | Remarks
Support for Maintenance activities | V | A
Request access needed for App environments support
Perform analysis and fix the assigned incidents and obtain Client acceptance on the methodology adopted by the maintenance team for completing the fix
Review fixes, resolutions provided by TCS
Support for Development activities | V | A
Review and approval of estimates
Refine Manuals | V | A
Review and release Documents of Understanding
Sign-Off | V | A
100% retention of all new Incidents (opened during shadow reverse phase).
Update the Transition Project Plan based on the project progress and changes in the scope of the project.
Support validation from current team (ACN)
Sign off Primary Support Phase
Activities for Acceptance
Activities | Vale |  | Approval by Vale | Remarks
Acceptance | V | A
signoff Document of Understanding
Transfer of responsibility to TCS